## Data
CUSTOMER | WORK ORDER NO | RATING | PRODUCTION TEAM | QTY | Planned dispatch | Weight in Kgs | REMARK | PRODN CLEARANCE | PO NO | DISPATCH DATE | DRAWING STATUS | OR COPY | PO Value | Lead time | Parts | Activities | Cutting | Fitup | Welding | inspection | PL | PTVT | LT | QC Clearance by | Blasting | painting | assembly | dispatch | Delay
ABB-POWER | 13159/1919 | 92MVA | 20 TON BAY | 4 OF 23 | 2021-01-15 | 15927 | Tanzania 92.2mva, | 2020-11-27 | 5191278039 | 2021-01-18 | 2020-10-22 | R | 2317032.6 | 49 | Part - A Qty: 2 nos | Planned | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | 3
[16 empty] | Actual | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Remarks
Rejection / Rework (drop down box)
Material, Qty, Man hours, Name
Estimated cost
[15 empty] | Part - B Qty: 9 nos | Planned | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
[16 empty] | Actual | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Remarks
Rejection / Rework (drop down box)
Material, Qty, Man hours, Name
Estimated cost
BRUSH | BT91160/1 | 20 MVA | 5 TON BAY | 1 of 2 | 2021-03-26 | 5988 | Export | 2020-12-25 | BT993081 | 2021-03-23 | 2020-12-25 | R | 14223.59 | 91 | Part - A Qty: 1 no | Planned | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | -3
[16 empty] | Actual | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Remarks
Rejection / Rework (drop down box)
Material, Qty, Man hours, Name
Estimated cost
[15 empty] | Part - B Qty: 5 nos | Planned | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
[16 empty] | Actual | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Remarks
Rejection / Rework (drop down box)
Material, Qty, Man hours, Name
Estimated cost

## Entry - Planning
Login | Team | Planning
| User Name | ---------
| Password | ******
| CUSTOMER | WORK ORDER NO | RATING | TEAM | QTY | Planned dispatch | Weight in Kgs | REMARK | PRODN CLEARANCE | PO NO | DRAWING STATUS | OR COPY | CURRENCY | PO Value | Lead time
| ABB-POWER | 13159/1919 | 92MVA | 20 TON BAY | 4 OF 23 | 2021-01-15 | 15927 | Tanzania 92.2mva, | √ | 5191278039 | √ | √ | INR | 2317032.6 | #VALUE!
| BRUSH | BT91160/1 | 20 MVA | 5 TON BAY | 1 of 2 | 2021-03-26 | 5988 | Export | √ | BT993081 | √ | √ | GBP | 14223.59 | #VALUE!
[9 empty] | On pressing the tick button, date has to be captured backhand | [5 empty] | To be computed from: G - J
| Team | Data visible under given header
| 10 TON BAY | Only 10 Ton Bay data
| 20 TON BAY | Only 20 Ton Bay data
| 40 TON BAY | Only 40 Ton Bay data
| 5 TON BAY | Only 5 Ton Bay data
| DT | Only DT data
| CB bay | Only CB bay
| B233 | Only B233
| BP 5 | All
| BP 20 | All
| Plasma | All
| Lazer | All
| SMS | All
| LMS | All
Admin rights | Admin | All
Admin rights | Planning | All
| AD | All
Admin rights | Maintenance | Only maintenance sreen

## Entry-Prodn head
Login | Team | 20 TON BAY
| User Name | #######
| Password | ******
Display Screen | CUSTOMER | WORK ORDER NO | RATING | QTY | Planned dispatch | Weight in Kgs | REMARK | PRODN CLEARANCE
1 | ABB-POWER | 13159/1919 | 92MVA | 4 OF 23 | 2021-01-15 | 15927 | Tanzania 92.2mva, | 2020-11-27
2
Entry form | Part | Sub Part | Nature of Work | Planned date | Actual date
| tank | left wall | Cutting | 29.11.2021 | To be captured from acual process completion dates from subsequent sheets
| cover | P1-1 | Fit up
| header | P1-2 | Welding
| P2 | .. | Grinding
| P3 | .. | Pipeline
| .. | .. | Others
Machining
| manual entry |  | Drop down
Authorizaton is required to edit above planned dates

## Entry-Prodn sup
Login | Team | 20 TON BAY
| User Name | XXXXXX
| Password | ******
Display Screen | CUSTOMER | WORK ORDER NO | RATING | QTY | Planned dispatch | Weight in Kgs | REMARK | PRODN CLEARANCE
1 | ABB-POWER | 13159/1919 | 92MVA | 4 OF 23 | 2021-01-15 | 15927 | Tanzania 92.2mva, | 2020-11-27
2
Entry form | Part | Sub Part | Nature of Work | Planned date | Work done by | Completion Date | Date / Time -Start | Date / Time -End | Total Hours | Delay | Reason for delay
| tank | left wall | Cutting | 29.11.2021 | xyz | √ | 0 | 0 | 0 | #VALUE! | Machine maintenance
| tank | RH Wall | Fit up |  | abc | √ | 0 | 0 | 0 | #VALUE! | Machine maintenance
| P1 | P1-2 | Welding |  | lkj | √ | 0 | 0 | 0 | #VALUE! | Absentism
| P2 | .. | Grinding |  | iuh | √ | 0 | 0 | 0 | #VALUE! | no material
| P3 | .. | Pipeline |  | xyz, abc | √ | 0 | 0 | 0 | #VALUE! | Re work
| .. | .. | Others |  | .. | .. | .. | .. | .. | #VALUE! | Others
| P1-RW | .. | Grinding |  | sdf | √ | 0 | 0 | 0 | #VALUE!
| The above data needs to be captured from -Sheet "Entry-prodn head" | [7 empty] | Backhand data
If completion date is greater than planned date, reason for delay needs to be entered
Till completion is entered, the work has to be dispalyed on the main screen with entry option
Once completed, the work has to be freezed / uneditable and highlited and gets sorted at bottom

## Entry-QC
Login | Team | 20 TON BAY
| User Name | OOOOO
| Password | ******
Display Screen | CUSTOMER | WORK ORDER NO | RATING | QTY | Planned dispatch | Weight in Kgs | REMARK | PRODN CLEARANCE
1 | ABB-POWER | 13159/1919 | 92MVA | 4 OF 23 | 2021-01-15 | 15927 | Tanzania 92.2mva, | 2020-11-27
2
Entry form | Part | Sub Part | Nature of Work | Inspection Result | Inspection Remarks | Date | Inspected by
| P1 | P1-1 | Fit up | OK | Re work |  | Auto generated from User ID (backhand data)
| P1 | P1-1 | Welding | Not OK | Rejection
| P1 | P1-2 | Grinding | Not OK | Conditionally accepted
| P2 | .. | Pipeline | OK | Others
| .. | .. | Others | ..
| P1-RW | .. | Grinding | ..
The above data needs to be captured from -Sheet "Entry-Prodn head"
If Inspection result is NOT OK, then Remarks & details needs to be entered in a pop up window
If inspection remark is rework, the part / subpart has to be reflected in Entry Prodn sup sheet with suffix RW. And additional box to be appreared to enter details of rework/mtrls.
If inspection remark is reject, the part / subpart has to be reflected in Entry Prodn sup sheet with suffix RJ. And additional box to be appreared to enter details of rejection / new mtrls used.
If inspection results are OK, then below activities to be done
| Part | Sub Part | Nature of Inspection | Inspection Result | Inspection Remarks | Date | Inspected by
| P1 | P1-1 | Visual | OK | Re work
| P1 | P1-2 | NDT | Not OK | Rejection
| P2 | .. | VTPT | Hold | Conditionally accepted
| P3 | .. | LT | NA | Others
| .. | .. | Others | Others
| P1-RW | .. |  | ..
Data captured from above table
If inspection results are OK, then part nos to be highlighted in green
If inspection results are NOT OK, then part nos to be highlighted in red & Remarks to be entered
If inspection results are HOLD, then part nos to be highlighted in Orange
Need option to add more inspection parameters

## Entry-Blasting Painting
Login | Team | BP5
| User Name | !!!!!!!!
| Password | ******
Display Screen | CUSTOMER | WORK ORDER NO | RATING | QTY | Planned dispatch | Weight in Kgs | REMARK | PRODN CLEARANCE
1 | ABB-POWER | 13159/1919 | 92MVA | 4 OF 23 | 2021-01-15 | 15927 | Tanzania 92.2mva, | 2020-11-27
2
Entry form | Part | Sub Part | Nature of Work | Work done by | Planned date | Completion Date | Date / Time -Start | Date / Time -End | Total Hours | Reason for delay | Inspection Result | Inspection Remarks | Inspected by
| P1 | P1-1 | Blasting | 1 | Entry-Prodn head'!E11 | 2021-12-04 | 0 | 0 | 0 | Machine maintenance | OK | Re work
| P1 | P1-2 | Primer | 2 |  | 2021-12-04 | 0 | 0 | 0 | Machine maintenance | Not OK | Rejection
| P2 | .. | Mid coat | 3 |  | 2021-12-04 | 0 | 0 | 0 | Absentism | Not OK | Conditionally accepted
| P3 | .. | Finish | 2,3 |  | 2021-12-04 | 0 | 0 | 0 | no material | OK | Others
| .. | .. | Others | .. |  | .. | .. | .. | .. | Re work | ..
| P1-RW | .. |  | 3 |  | 2021-12-04 | 0 | 0 | 0 | Others | ..
| The above data needs to be captured from -Sheet "Entry-Prodn sup" | [7 empty] | Backhand data
Date needs to be choosen from calander. Posting dated to be recorded backhand
How ? | Rework / Rejection activities to be identified separately and traceable
How ? | Rework hour - additional material used needs to be traced
Only Inspection OK parts to be visible in next screen
If inspection results are NOT OK, then part nos to be highlighted in red & Remarks to be entered
If inspection results are HOLD, then part nos to be highlighted in Orange
Till inspection is OK, the work has to be dispalyed on the main screen with entry option
Once completed, the work has to be freezed / uneditable and highlited and gets sorted at bottom

## Entry-Assembly & Dispatch
Login | Team | AD
| User Name | ^^^^^^
| Password | ******
Display Screen | CUSTOMER | WORK ORDER NO | RATING | QTY | Planned dispatch | Weight in Kgs | REMARK | PRODN CLEARANCE
1 | ABB-POWER | 13159/1919 | 92MVA | 4 OF 23 | 2021-01-15 | 15927 | Tanzania 92.2mva, | 2020-11-27
2
Entry form | Part | Sub Part | Nature of Work | Work done by | Date | Time -Start | Time -End | Total Hours | Inspection Result | Inspection Remarks | Inspected by | Disaptch date
| P1 | P1-1 | Identification | 1 | 2021-12-04 | 0 | 0 | 0 | OK | Re work
| P1 | P1-2 | Stud assembly | 2 | 2021-12-04 | 0 | 0 | 0 | Not OK | Rejection
| P2 | .. | Retapping & Antirust application | 3 | 2021-12-04 | 0 | 0 | 0 | Not OK | Conditionally accepted
| P3 | .. | Packing | 2,3 | 2021-12-04 | 0 | 0 | 0 | OK | Others
| .. | .. | Others | .. | .. | .. | .. | .. | ..
| P1-RW | .. |  | 3 | 2021-12-04 | 0 | 0 | 0 | ..
Only inspection OK parts will be visible above
If inspection results are OK then dispatch date to be entered

## Reports
| Total report | [9 empty] | 1
| CUSTOMER | WORK ORDER NO | RATING | PRODUCTION TEAM | QTY | Planned dispatch | Weight in Kgs | REMARK | PRODN CLEARANCE | PO NO | ACTUAL DISPATCH DATE | DRAWING STATUS | OR COPY | CURRENCY | PO Value | Lead time | Status as on date | Delay | More
| ABB-POWER | 13159/1919 | 92MVA | 20 TON BAY | 4 OF 23 | 2021-01-15 | 15927 | Tanzania 92.2mva, | 2020-11-27 | 5191278039 | 2021-11-15 | 2020-10-22 | R | INR | 2317032.6 | 49 | Click here | 304 | Click here
2021-11-25
1 | Actual dispatch date has to be taken from sheet assembly & dispatch
| If dispatch is done in multiple lots, different dates to be apprared as per dispatch sheet | [16 empty] | CUSTOMER | WORK ORDER NO | PRODUCTION TEAM | QTY | Weight in Kgs | Total Man hours | Re Work hours
[18 empty] | ABB-POWER | 13159/1919 | 20 TON BAY
Sales projection
| Month | Customer | Po No | Work Order no | Qty | Weight | Value (in PO currency)
** | Based on planned dispatch
Full screen of completion
| Sales report | [15 empty] | Part | Sub Part | Nature of Work
| Month | Customer | Po No | Work Order no | Qty | Weight | Value (in PO currency) | [9 empty] | tank | left wall | Cutting
** | Based on actual dispatch | [15 empty] | tank | RH Wall | Fit up
[17 empty] | P1 | P1-2 | Welding
[17 empty] | P1-RW | .. | Grinding
WIP report
| Enter Currency conversion rate (manual entry in table) |  |  |  |  | 2 | [10 empty] | On the current date, which ever PARTS - SUB PARTS has completed the stages, that stage has to be appeared.
| Month | Customer | Work Order no | SFG Price/kg (INR) | Qty(set) | % completion | Finished Weight (drg ) in Kgs/set | Total Processed Weight in kgs | Item Value (PO Currency) | Conversion Rate | Processed Value (in INR)
|  |  |  | 175.2684 | 1 | 85 | 16200 | 15147 | 54925 | 73.85 | 3447779.5625
2 | % completion is defined as below
| If status as on date = | % Value
| Fit up | 55
| Pipe line assy | 85
| Machining | 85
| Painting | 95
If majority of parts / subparts has completed, pipeline assy stage, it has to pick 85 % ( as defined in the table).
Table content should be editable for Admin
Note on B22: USD = EURO = GBP = INR =1

## General Requirements
1 | All dates needs to be selected from calander / list
2 | All time needs to be selected from list
3 | All posting date, time and user should be captured backhand
4 | Dates needs to be sorted / filtered in terms of year -> month (similar to excel sheet)
5 | View mode required to see, sort & filter all datas.
6 | Filter option is required for cells highlighted in yellow
7 | All datas (including backhand datas) should be able to extract to excel sheets

## Maintenance
Login | Team | Maintenance
| User Name | +++++++
| Password | ******
| Date | Machine No. | Name of Machine | Section | Type of service | Nature of problem | Attended By | Spares used | Qty | Time-start | Time-end | No. of Hrs | Remarks
|  | m 282a w1 |  |  | AMC | Electrical spares problem | [6 empty] | Work Completed
[5 empty] | PM | Mechanical spares problem | [6 empty] | Work in process
[5 empty] | BDM | Electronics spares problem | [6 empty] | Work inprocess and spare m/c given
|  | Auto suggestion to sort on basis of w1, w2 |  |  | New Installation | Softwares problem | [6 empty] | Others
[5 empty] | Others | Others